## Sheet1
Risk Analysis
Task Name | Duration | Start time | Finish Time | Resource | Probablity | Impact | Risk Level | Risk Severity
Communication | 8 days | Mon 10/17/22 | Wed 10/26/22 | Project manager | Medium Low | High | Medium Low | High
Planning | 4 days | Thu 10/27/22 | Tue 11/01/22 | Project manager | Low | Medium High | High | Medium High
Modeling | 9 days | Mon 11/07/22 | Thu 11/17/22 | Designer | Medium Low | Medium High | Medium High | Medium Low
Construction | 10 days | Sat 11/19//22 | Tue 11/29/22 | Programmer & Tester | Medium High | Medium Low | Medium | Medium Low
Deployment | 1 day | Wed 11/30/22 | Wed 11/30/22 | Customer & PM | Low | Medium | Medium Low | Low
Effort estimation | 1 day | Thu 10/27/22 | Thu 10/27/22 |  | Medium High | High | Medium High | Medium
Activity Planning | 6 days | Mon 11/14/22 | Sat 11/19/22 | PM | High | High | Medium High | High
Resource Allocation | 5 days | Sun 11/20/22 | Thu 11/24/22 |  | Medium Low | Medium Low | Low | Low